Progress Update – Walpole Broadband Project

December 28, 2020

| Job | Fiber Built % | Splicing % | Testing Complete | Ready for Install |
| --- | --- | --- | --- | --- |
| Gray-Bellows Falls FDH #1 | 100% | 100% | In Progress | Not Started |
| Light Pink-Bellows Falls FDH #2 | 100% | 100% | In Progress | Not Started |
| Light Green-Bellows Falls FDH #3 | 100% | 50% | Not Started | Not Started |
| White-Bellows Falls FDH #4 | 100% | 25% | Not Started | Not Started |
| Orange-Walpole FDH #1 | 95% | 75% | Not Started | Not Started |
| Purple-Walpole FDH #2 | 95% | 75% | Not Started | Not Started |
| Red-Walpole FDH #3 | 95% | 75% | Not Started | Not Started |
| Lime Green-Walpole FDH #4 | 95% | 75% | Not Started | Not Started |
| Light Blue-Walpole FDH #5 | 95% | 65% | Not Started | Not Started |
| Yellow-Walpole FDH #6 | 95% | 65% | Not Started | Not Started |
| Dark Blue-Walpole FDH #7 | 95% | 50% | Not Started | Not Started |